Report 99.143

20 March 1999

File: N/6/13/2

Report to the Landcare Committee

from Graeme Campbell, Project Manager, Flood Protection (Strategy and Assets)

Waikanae Floodplain Management Plan

Kauri-Puriri Flood Mitigation Measures : Project Completion Report

1.	Purpose

To advise the Landcare Committee that the Kauri-Puriri Flood Mitigation Measures project is now complete.

2.	Background

The need for the Kauri-Puriri Flood Mitigation Measures was identified in the early stages of preparing the Waikanae Floodplain Management Plan.  The works were considered of such importance that they should proceed ahead of the Plan completion.  Budget provision was made in the 1995/96 and 1996/97 financial years for the works.  Preparatory work began in July 1995 with the appointment of the Project Manager, Graeme Campbell, who has managed the project through to completion.

3.	Design/Consents

The preparation of detailed design and consent applications for the Kauri-Puriri works started in February 1996, with the appointment of AC Consulting Group.  Design work was completed on programme, but the granting of consents was delayed by an appeal to the environment court by an adjacent land owner.  The appeal was finally withdrawn in mid December 1996, allowing tenders for construction to be let to John Ray Ltd at the end of December 1996.   AC Consulting were appointed to undertake the construction management following the successful completion of the design stages and resolution of the consent appeal.

4.	Construction

Construction started in mid January 1997, approximately two months behind schedule, due to the delay caused by the appeal to the Resource Consent.  The contractor was able to make this time up during the course of construction, with the river works being finished by the end of April 1997 and the certificate of substantial completion for all works being issued on 30 June 1997.  No substantive matters arose during the 12 month maintenance period and the maintenance certificate was issued on 30 June 1998.  The 17th and final contract payment was made in August 1998.

An official opening for the project was held in November 1997 with the area being named “Pukekawa Reserve”.  The opening was attended by approximately 100 people and was an indication of the support the project had received from the community, and their approval of the works.

An agreement between Kapiti Coast District Council and the Wellington Regional Council for the joint maintenance of the area, is now in place.

5.	Programme and Budget

The project was completed $63,000 under the original $1.47 million budget, set in early 1994.  Inflation over the span of the project was in the order of five percent, or $75,000; to finish under budget is considered a good result.  A breakdown of the budget is included in Attachment 1.

The works were completed within programme as noted above.  A detailed programme (planned and actual) is included in Attachment 2.

6.	October 1998 Flood Events

Two flood events occurred in October 1998 and the works performed as designed with minimal damage to the site.  This was an excellent result, given that the floods were 30 and 15 year return period events respectively.  Both floods would have overtopped the old stopbank and resulted in one to two million dollars of damage to property and infrastructure.  This is one of those rare occasions where the payback (full recovery of project costs) is received within a year of completion of construction.  The minor tidy up works, required following the floods, have now been completed at a cost of $5,000.

7.	Recommendation

That the Landcare Committee receive this report and note its contents.

Report prepared by:	Approved for submission:

GRAEME CAMPBELL	BRENDAN PAUL

Project Manager	Manager, Flood Protection (Strategy and Assets)

ANDREW ANNAKIN

Divisional Manager, Landcare

Attachment 1 : Summary Budget

Attachment 2 : Planned and Actual Project Programme

Summary Budget